Organising a Track & Field Meet Checklist

| Timeline | Tasks | Completed |
| --- | --- | --- |
| Well in advance (6-9 months) | Within your club, decide on provisional date and events. Get as many volunteers and officials from within your club as possible and confirm they are prepared to help. |  |
|  | Contact ANI office with details of provisional arrangements and request for any support required e.g. extra officials, online entries etc. |  |
|  | Wait for approval of arrangements from ANI. |  |
| Once approval in received | Carry out risk assessment. |  |
|  | Apply for permit from ANI. This will be pending until numbers of officials are confirmed. A provisional timetable must also be submitted with your permit. |  |
|  | Provisionally book the venue and first aid cover. |  |
|  | Order numbers & pins. If required order medals/prize and field cards |  |
| 6 weeks before event | If ANI officials are required, the timetable should be sent to ANI Officials Co-ordinator. |  |
|  | Timetable to be sent to venue. |  |
| 4 weeks before event | Confirm the timetable and publish it on social media/club, website/ANI website etc. |  |
|  | Entry system opens and should close 10 days before event. |  |
| 10 days before event | Allocate athlete bib numbers. |  |
|  | Seed track athletes and complete lane draws. |  |
|  | Arrange procedure for results, live stream, live results print out. |  |
| 5 days before event | Send final timetable, lane draws and athlete bib number to the photofinish team and announcer. |  |
|  | Write/print field cards - two copies of each card. |  |
|  | Arrange for refreshments for officials. Tea/coffee biscuits for half day meeting. Lunch for full day meeting. |  |
| 2 days before event | Arrange for venue electrical equipment to be charged. EDM for field events, TESS starting system, Walkie Talkies |  |
|  | Print out copy of the start lists for Announcer, Start Team, Photo Finish Team, Track Referee and Track Staff. |  |

Organising a Track & Field Meet Checklist

| Day of event | Arrive early! |  |
| --- | --- | --- |
|  | Display bib numbers, timetables, lane draws etc around the venue |  |
|  | Club volunteers to set up registration for athletes-Issue bib number and pins. |  |
|  | Have Walkie Talkies available for Meeting Organiser, First Aid, Announcer, Photo Finish, Starter, Track Referee, Field Referee, Results. |  |
|  | Have field cards ready for the Field Referee. |  |
|  | Set up Officials refreshment area. |  |
|  | Organise presentations if required. Work with announcer. |  |
|  | Organise results team. A volunteer should be available to display results on a notice board if this is the results method being used. |  |
| After Meeting | Tidy up venue. |  |
|  | Send results to ANI office as soon as possible. |  |

Useful Links & Contacts

ANI Event & Marketing Team: info@athleticsni.org, marketing@athleticsni.org, shauna.bratten@athleticsni.org

ANI Permit Process: www.athleticsni.org/Permits/

ANI Fixtures: www.athleticsni.org/Fixtures

ANI Technical Officials: officials@athleticsni.org

ProParamedics: www.proparamedics.com

Ambutran: ambutran@yahoo.co.uk or 07711096370

St John Ambulance: www.sja.org.uk

Mary Peters Track: www.marypeterstrack.com

Antrim Forum: https://antrimandnewtownabbey.gov.uk/leisure-centres/activities/track-running/